## Overview
Gym for Murrumbeena — Campaign at a Glance
A School Council community campaign to win ~$12–14M of state funding for a competition-grade community gym. 15 months (Sep 2026 – Nov 2027), three phases, community-funded. Figures are indicative estimates.
Phase 1 | Election Promise | 7 Sep – 2 Nov 2026 (8 wks) | Launch petition + website, gather endorsements, signs, billboard, door-knocks, brochures; ask every party for a written commitment
Phase 2 | Election Window | 3 – 28 Nov 2026 (4 wks) | Community campaigning continues through the caretaker freeze; 'Hall for All' rally + fundraising sizzle on election day
Phase 3 | Post-Election | Dec 2026 – Nov 2027 (12 mo) | Hold the new government to its promises, re-lodge the petition, meet the Minister, press for the May 2027 Budget; month-12 review
Deliverables | Parliamentary e-petition, Action Hub website, campaign pack + fact sheets, 250 corflute signs, 2 school-fence banners, billboard (4 wks), 1,000 postcards, 2 letterbox drops (~5,000 homes), door-knocking (2,000+ doors), Coalition Dossier (25+ endorsements), kids' letter bundles, social posters + videos, election-day rally + sausage sizzle, post-election Budget submissions
Group Size | 1. Campaign Chair — strategy, political liaison, spokesperson (6–8 h/wk) 2. Deputy Chair / Secretary — minutes, calendar, roster (3–4) 4. Digital Lead — website, petition, email tool (4–6) 5. PR / Media Lead — pitches, releases, billboard (4–6) 6. Ground-Game Lead — signs, door-knocks, drops, stalls (4–6) 7. Events Lead — rally + sizzle (3–5) 8. Community Liaison — club & business endorsements (3–4) 9. Parent Comms — parent emails, class reps (2–3) 10. Creative Lead — posters, videos, photos (3–5) 11. School Liaison — school interface, kids' letters (2–3) 12. Legal / Compliance Advisor — authorisations (as needed)
Metrics | PRE-ELECTION (by 28 Nov 2026): • ≥ 1 written party commitment • 2,500+ petition signatures • 25+ community endorsements • 250 signs up, 2,000+ doors knocked • 400+ people at the election-day rally POST-ELECTION (to Nov 2027): • Minister meeting within 60 days • Gym in the 2027–28 State Budget (May 2027) • 80% of coalition still engaged at month 12 • Month-12 review: funded → delivery watch; not funded → low intensity
Budget | ≈ $9,500–12,000

## Working Group
Working Group
Role | Name | In charge of | Weekly load
Campaign Chair | Jenks Guo | Strategy, political letters/sign-offs, party liaison, dossier deliveries, spokesperson #1 | 6–8 h
Deputy Chair / Secretary |  | Minutes (MO 1280), calendar, gate checklists, volunteer roster master | 3–4 h
Digital Lead |  | Action Hub, e-petition, 1-click email tool, analytics, QR links | 4–6 h
PR / Media Lead (vacant — recruit W1) |  | Media list, pitches, releases, spokesperson prep, billboard creative | 4–6 h
Ground-Game Lead |  | Corflutes, door-knock pairs, letterbox drops, stall logistics, VEC signage compliance in the field | 4–6 h
Events Lead + deputy |  | Rally, sausage sizzle (permits, food safety, floats), stalls | 3–5 h (peaks at events)
Community-Liaison Lead |  | Clubs, trade groups, businesses, community hubs; endorsement letters; coalition care | 3–4 h
Parent-Comms Lead |  | Parent emails, class-rep network, poster/video share kits | 2–3 h
Creative Lead |  | Posters, testimonial videos, photography, consent forms for student imagery | 3–5 h
School Liaison |  | DET interface: principal briefings, regional-director notifications, visit protocols, kids' letters program with teachers | 2–3 h
Legal / Compliance Advisor (pro bono) | Deb | VEC authorisation sign-offs, DET policy interface, defamation check on anything naming individuals | as needed
Advisors
Role | Name | In charge of | Capacity
Campaign | Carolin Thorton
Legal | Katerina

## Gift List
# | Gift-list item | Spec | Unit est. | Qty | Est. total
1 | Corflute yard sign (sponsor-a-sign) | 900×600, QR to petition | $10–12 | 250 | 3000
2 | School-fence banner | 3×1 m mesh, DET-compliant | 300 | 2 | 600
3 | "Voices of Murrumbeena" postcards | A5 full-colour | 0.35 | 1000 | 350
4 | Letterbox brochures | A4 tri-fold or DL | 0.15 | 5000 | 750
5 | Billboard (suburban 6×3 static, 4 weeks) | community rate if possible | $2,500–5,000 | 1 | 5000
6 | Action Hub domain + hosting + email tool | 12 months | 250 | 1 | 250
7 | Testimonial video production | volunteer edit + captions/music licences | 150 | 1 | 150
8 | Rally day (AV hire, permits, insurance, signage) | 2026-11-28 | 800 | 1 | 800
9 | Dossier printing & binding | colour, 20 copies | 10 | 20 | 200
10 | Door-knock kits (clipboards, QR cards, badges) | per-pair kit | 15 | 20 | 300
11 | Social media boosting (pre-1 Oct only, lawyer sign-off) | capped | 500 | 1 | 500
| TOTAL |  |  |  | 11900

## Metrics
Pre-election (by 28 Nov 2026)
Metric | Target
Written, party-authorised funding commitments | ≥2 parties (≥1 before caretaker 3 Nov)
Parliamentary e-petition signatures | ≥2,500 (stretch 3,000)
Organisational endorsements in dossier | ≥25 (incl. 5 clubs, 3 trade/professional, 3 community hubs)
Corflutes deployed on arterial streets | 250
Doors knocked | ≥2,000
Letterbox drops | 2 × ~2,500 homes
Media hits (local + state) | ≥6
Rally + sizzle attendance / funds | ≥400 people / ≥$1,500 raised
Kids' letters delivered | ≥300
Candidate school visits completed | ≥3 (equal access protocol)
Post-election (Dec 2026 – Nov 2027)
Metric | Target
Meeting with incoming Minister / local member | within 60 days of result
VSBA 2027–28 business-case inclusion (condition track) | by mid-2027
Named in Glen Eira Community Infrastructure Plan | 2026–27 adoption cycle
2027–28 State Budget line for the gym (May 2027) | the hinge metric
If missing out: media ops executed within 48 h of Budget | 100% execution
Petition total by anniversary | ≥3,000
Coalition retention (orgs still engaged at month 12) | ≥80%
Month-12 review completed with sustain/dormancy decision | 46692

## Timeline
Campaign Timeline Tracker |  |  | Completion
0%
Phase | Timeframe | Task Description | Status | Owner | Notes
PHASE 1 — ELECTION PROMISE PHASE | Week 1 · 7–13 Sep | Action Hub micro-site live (hallformurrumbeena.com.au or Linktree + QR): hall photos, renders, comparators (Carnegie, Glen Huntly), two buttons — **Sign the e-petition** / **1-click email to MPs**. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 1 · 7–13 Sep | Request parliamentary e-petition sponsorship (Dimopoulos; fallback Crozier MLC). Target 2,500+ verified signatures. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 1 · 7–13 Sep | Send support-letter requests: Murrumbeena Netball Club, Murrumbeena Junior FC, Carnegie Chargers, McKinnon Basketball Assoc., Rotary Caulfield, traders association, TheirCare, GEKA, nearby community hubs (Murrumbeena Uniting, community centres). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 1 · 7–13 Sep | Order 250 corflutes + 1,000 "Voices of Murrumbeena" postcards (VEC authorisation line; lawyer sign-off on artwork). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 1 · 7–13 Sep | Parent email #1 (campaign launch, petition link). Working group roles confirmed; MO 1280 minute filed. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 2 · 14–18 Sep | School-fence banner installed (Hobart Rd frontage; DET-compliant, issue-based wording). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 2 · 14–18 Sep | Postcards home with every student; class reps push blurb + 1-click email link. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 2 · 14–18 Sep | **22-letter pack** sends begin (councils, candidates, MLCs, federal MPs). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 2 · 14–18 Sep | Media pitch #1 — "postcode lottery in the Sport Minister's own seat" (Glen Eira News, Monash Bulletin). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 2 · 14–18 Sep | Kids' letters project announced to classes: letters/art to the Premier and the Education Minister. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Weeks 3–4 · 21 Sep – 4 Oct | Sea of Signs: 250 corflutes on family homes along Murrumbeena Rd, Neerim Rd, Poath Rd, Hobart Rd, Kangaroo Rd. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Weeks 3–4 · 21 Sep – 4 Oct | Billboard: book suburban 6×3 site (4-week slot covering Weeks 5–8); artwork finalised and lawyer-approved. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Weeks 3–4 · 21 Sep – 4 Oct | Film testimonial videos (school captains, netball coaches, parents) for socials; poster set for parent sharing. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Weeks 3–4 · 21 Sep – 4 Oct | Collate endorsement letters into the **Coalition Dossier** (clubs, trade/professional associations, businesses, community hubs). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Weeks 3–4 · 21 Sep – 4 Oct | Door-knock scripts + maps prepared; volunteer roster built. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 5 · 5–11 Oct | Postcard collection begins; stalls at Murrumbeena Station/village and Koornang Rd (Sat). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 5 · 5–11 Oct | **Billboard live.** Letterbox brochure drop #1 (school zone, ~2,500 homes). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 5 · 5–11 Oct | Parent email #2 (petition milestone push + poster/video share kit). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 5 · 5–11 Oct | Formal rally invitations to Dimopoulos, Liberal candidate, Greens candidate. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 6 · 12–18 Oct | Door-knocking weekends begin (streets around the school; 60-second script; QR cards). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 6 · 12–18 Oct | 1,500-signature milestone media note; e-petition promoted in final sitting weeks. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 6 · 12–18 Oct | Kids' letters collected and bundled (ribbon-tied boxes for Premier + Education Minister). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 6 · 12–18 Oct | Club/association/trade-group letters finalised; dossier printed. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 7 · 19–25 Oct | Letterbox drop #2 (school zone + Carnegie–Hughesdale fringe). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 7 · 19–25 Oct | Media pitch #2 — sub-floor plumbing / public-health angle; VSBA "Poor (3.1)" condition rating. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 7 · 19–25 Oct | Candidate briefing sessions on site (equal access — DET visit protocol, 5-day regional-director notice). | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 7 · 19–25 Oct | Polling-day rally plan locked: site layout, BBQ fundraising permits, VEC 100 m signage plan, volunteer roster. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 8 · 26 Oct – 2 Nov | Open-letter ad / social ad: "Before Parliament rises: who will back Murrumbeena?" | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 8 · 26 Oct – 2 Nov | Coalition Dossier delivered to Minister Williams and Shadow Minister Rowswell; final written-commitment requests to all parties. | Not Started
PHASE 1 — ELECTION PROMISE PHASE | Week 8 · 26 Oct – 2 Nov | **GATE (2 Nov):** target ≥1 written party commitment; 2,500 signatures; 25+ endorsements. | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Weeks 9–10 · 3–17 Nov | Government frozen; **opposition pledges continue** — keep chasing Liberal/Greens written commitments. | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Weeks 9–10 · 3–17 Nov | Corflutes stay up; door-knocking and social videos continue (VEC authorisation on everything). | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Weeks 9–10 · 3–17 Nov | Kids' letter bundles delivered to candidates' offices with photo op. | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Week 11 · 18–27 Nov | Compliant presence near early-voting centres (100 m signage rule enforced; assume MPS is a voting centre). | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Week 11 · 18–27 Nov | Final share push: testimonial videos, "who has committed?" scorecard (factual, identical treatment of all parties). | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Polling Day · Saturday 28 Nov | Community rally on school grounds / Murrumbeena Park, timed with polling-day foot traffic. | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Polling Day · Saturday 28 Nov | **Fundraising sausage sizzle + cake stall** running all day (school-council fundraising rules; floats and receipts logged). | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Polling Day · Saturday 28 Nov | Giant signature floor banner; student performances; junior shootouts; candidate attendance invited (equal access). | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Polling Day · Saturday 28 Nov | Media invited: "on election day, this school is still waiting for its hall." | Not Started
BRIDGE — CARETAKER & POLLING WINDOW | Polling Day · Saturday 28 Nov | Compliance: no election signage within 100 m of the voting entrance during voting hours; all material authorised; principal-neutral execution. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 1 · Dec 2026 | Within 48 h of the result: **if committed/funded** → congratulatory hold-to-account letter quoting the written commitment, delivery timeline request. **If missing out** → **Media Op #1**: "the forgotten school in the Sport Minister's backyard" release + opposition response invite. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 1 · Dec 2026 | Thank-you campaign to all supporters; petition snapshot; summer evidence completion (CAR, QS opinion, measured survey). | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 2 · Jan 2027 | No public ops. Refresh evidence file; coalition check-ins; plan February re-launch. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 3 · Feb 2027 | Re-lodge parliamentary e-petition in the new Parliament (sponsor MP). | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 3 · Feb 2027 | Meeting requests: (new) Minister for Education, local member, Shadow Minister; VSBA Door-2 condition-track submission refreshed for the 2027–28 business case. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 4 · Mar 2027 | Dossier to Treasurer / ERC consideration channels; updated club letters with season data. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 4 · Mar 2027 | Parent email #3; school-council motion reaffirming the campaign. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 5 · Apr 2027 | Petition push to 3,000 (St Kilda benchmark); budget-eve media piece; council CIP inclusion check. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 6 · May 2027 | **If funded:** victory comms, thank-yous, transition to delivery-watch (design consultation, CJUA negotiation, community access terms). | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 6 · May 2027 | **If missing out:** **Media Op #2 (the big one)** — same-day release, opposition question in Parliament, Estimates-hearing questions lodged via Southern Metro MLCs, "81% of Poor schools stay Poor" angle, second rally consideration. Petition surge drive. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Months 7–8 · Jun–Jul 2027 | VAGO report anniversary (17 Jun): condition-story repitch; PAEC Estimates follow-up. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Months 7–8 · Jun–Jul 2027 | Winter content: kids training in the rain; netball season waitlist data; federal Thriving Suburbs R2 application if the round opens. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Months 9–10 · Aug–Sep 2027 | Campaign 1-year anniversary: progress report to community, media retrospective ("one year on, still a 1996 hall"), refreshed petition surge, new-school-year parent intake recruitment. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 11 · Oct 2027 | Refreshed asks and updated costings (annual escalation); new condition data if published; briefings with all parties for the 2028–29 cycle. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 12 · Nov 2027 | Committee decision point: | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 12 · Nov 2027 | **Funded** → close the campaign; convert to delivery-watch sub-committee (quarterly cadence). | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 12 · Nov 2027 | **Not funded** → choose: sustain at low intensity (annual rhythm: budget-window ops only) or dormancy with asset archive. | Not Started
PHASE 2 — POST-ELECTION PROCESS PHASE | Month 12 · Nov 2027 | Archive: contact lists, dossier, creative assets, research files; final report to School Council; wind-down of spend. | Not Started

## Deliverables
Deliverable | Production | Live / in field | Owner
Core arguments & research pack | W1 (already drafted; condition-led update) | W1 → ongoing refresh | Chair + research
Campaign pack (fact sheet, Q&A, media kit) | W1 | W2 | PR lead
Petition site (parliamentary e-petition + mirror) | W1 | W1 | Digital lead
Action Hub site (testimonials + gift list) | W1 build; testimonials added W3–4 | W1 | Digital lead
Club & association support letters | requested W1; due W4 | dossier W6 | Community-liaison lead
Trade-group / professional association letters | requested W1–2; due W5 | dossier W6 | Community-liaison lead
Nearby community hub support letters | requested W2; due W5 | dossier W6 | Community-liaison lead
Billboard (1 × 6×3 suburban, 4 weeks) | artwork W3–4 | W5–8 | PR lead + Treasurer
Sea of Signs — 250 corflutes | print W1–2 | deployed W3–4; maintained to 28 Nov | Ground-game lead
Door-knocking operation | roster W4 | W6–8, W9–11 (weekends) | Ground-game lead
Letterbox brochure drops × 2 (school zone) | print W4 | drop #1 W5; drop #2 W7 | Ground-game lead
Polling-day rally + sausage sizzle | plan W7; permits W7–8 | 2026-11-28 | Events lead
Parent email messaging ×3 | W1, W5, Mar 2027 | as scheduled | Parent-comms lead
Kids' letters to Premier + Education Minister | collect W2–W6 | delivered W9–10 | School liaison
Parent social posters + testimonial videos | film/design W3–4; weekly posts | W4 → 28 Nov; monthly in Phase 2 | Creative lead
Coalition Dossier (bound, all endorsements) | W6 | delivered W8; refreshed Feb–Mar 2027 | Chair